## Procurement WBS
Procurement work breakdown structure
Source: Programming Test v4 (1).pdf, pages 1 and 3. Implemented scope and operational limits: docs/scope.md.
WBS ID | Module | Feature | Work package | Owner / actor | Acceptance / deliverable | Source path
1.1 | Analysis | Business process | Define request, approval, PO and acceptance flow | Analyst | BPMN PDF and editable swimlane diagram | docs/procurement-bpmn.pdf
1.2 | Analysis | Scope and roles | Map v4 requirements and explicit business boundaries | Analyst | Role matrix and v4 scope | docs/scope.md
1.3 | Analysis | Work breakdown | Map modules and features to deliverables | Analyst | Excel module and feature breakdown | docs/procurement-wbs.xlsx
2.1 | Identity | Sign in and out | Authenticate four fixed roles; expire signed sessions | All roles | Valid login opens role-specific workspace | procurement/auth.py
2.2 | Identity | Access control | Check role and ownership at every action | Server | Unauthorized roles and owners are denied | procurement/workflow.py
2.3 | Identity | Request protection | CSRF, escaping, password hashing and login throttling | Server | Forged POSTs and repeated logins are blocked | tests/test_v4.py
3.1 | Requests | Create draft | Capture purpose, category, priority and required date | Requester | Draft with 1-20 validated line items | procurement/workflow.py
3.2 | Requests | Estimated budget | Calculate quantity times integer-rupiah unit price | Server | Budget is derived from lines on the server | procurement/workflow.py
3.3 | Requests | Submit | Validate draft state and required date | Requester | Only the owner can submit a draft | procurement/workflow.py
3.4 | Requests | Full revision | Edit fields, date and lines; preserve submitted snapshots | Requester | New revision clears previous approval | procurement/workflow.py
3.5 | Requests | Cancellation | Cancel any request before a PO is issued | Requester | Terminal cancellation before ordering | procurement/workflow.py
4.1 | Approval | Review queue | List submitted requests and inspect full detail | Approver | Queue shows requests awaiting a decision | frontend/src/features/requests/request-list.tsx
4.2 | Approval | Decision | Approve or return with reason; prevent self-approval | Approver | Decision is recorded atomically | procurement/workflow.py
4.3 | Approval | Revision binding | Approve the exact submitted request content | Approver | Changed content invalidates prior approval | procurement/workflow.py
5.1 | Purchasing | Supplier directory | Add supplier references and select an existing supplier | Purchasing | Unknown or duplicate suppliers rejected | procurement/purchasing.py
5.2 | Purchasing | Quotation lines | Capture quotation reference, lead time and line prices | Purchasing | Prices are distinct from request estimates | procurement/purchasing.py
5.3 | Purchasing | Purchase order | Create one itemized PO using a current quotation | Purchasing | Snapshot supplier, quantities and agreed prices | procurement/purchasing.py
5.4 | Purchasing | Quotation comparison | Compare supplier price and delivery lead time | Purchasing | Record an explicit supplier-selection reason | frontend/src/features/purchasing/quotation-comparison.tsx
5.5 | Purchasing | Printable purchase order | Render issued supplier and price snapshots | All roles | Print or save a PO with its agreed line prices | frontend/src/features/purchasing/purchase-order.tsx
6.1 | Receiving | Incoming deliveries | Show ordered and partially received requests | Receiver | Outstanding states are discoverable | frontend/src/features/requests/request-list.tsx
6.2 | Receiving | Inspection acceptance | Record accepted quantities and delivery reference | Receiver | Positive accepted quantity; no over-receipt | procurement/receiving.py
6.3 | Receiving | Partial completion | Keep incomplete PO lines outstanding for later delivery | Server | Received only when every line is complete | procurement/receiving.py
6.4 | Receiving | Duplicate protection | Operation tokens, delivery references and locking | Server | Concurrent receipts cannot over-count | tests/test_v4.py
7.1 | Workspace | Overview | Aggregate counts in SQL; paginate requests | All roles | Visible scope respects ownership | procurement/workflow.py
7.2 | Workspace | Search and filters | Search titles or PR IDs; filter workflow states | All roles | Parameterized queries return matching rows | procurement/workflow.py
7.3 | Workspace | Responsive interface | Adapt navigation, forms and tables to screen width | All roles | Labels, focus states and scrolling tables | frontend/src/index.css
8.1 | Traceability | Audit history | Record actor, action, note and UTC timestamp | Server | Business changes and audit commit together | procurement/models.py
8.2 | Traceability | Order and delivery detail | Show supplier, quotation, PO and delivery history | All roles | Authorized readers can trace fulfillment | frontend/src/features/requests/request-detail.tsx
9.1 | Data | Schema and constraints | Normalize requests, revisions, quotes, orders and receipts | Server | Foreign keys, checks and unique references | procurement/models.py
9.2 | Data | Atomic transitions | Validate and write in one immediate transaction | Server | Failed mutations roll back completely | procurement/db.py
9.3 | Data | Demo setup | Atomically seed roles, suppliers and relative-date examples | Developer | Populated database is never overwritten | procurement/seed.py
9.4 | Data | Versioned migrations | Adopt legacy v1 and apply Alembic schema revisions | Developer | Preserve history without inventing old prices | migrations/versions/
10.1 | Quality | Regression tests | Run unchanged against SQLite and PostgreSQL | Developer | Workflow, HTTP and concurrency tests | tests/test_v4.py
10.2 | Quality | Run and review guide | Document setup, demo, limits and submission files | Developer | Repository can be cloned and run locally | README.md
10.3 | Quality | Continuous integration | Check format, typing and database regressions | Developer | CI covers both supported database engines | .github/workflows/checks.yml
10.4 | Quality | Browser regression | Exercise roles, procurement flow and mobile layout | Developer | Opt-in browser tests with failure traces | tests/test_browser.py
10.5 | Quality | Architecture decisions | Explain transaction, revision and extraction boundaries | Developer | Decisions and limitations are reviewable | docs/decisions.md
10.6 | Quality | Debugging evidence | Record a reproduced migration constraint defect | Developer | Root cause, fix and regression are linked | docs/debugging.md
11.1 | Document input | Protected upload | Validate PDF/image content and bounded size | Purchasing | Private storage and authorized file access | procurement/documents.py
11.2 | Document input | Local PDF parser | Extract explicitly labeled PDF fields without a provider | Purchasing | Clearly labeled as text parsing, not AI/OCR | procurement/extraction.py
11.3 | Document input | Optional AI extraction | Use structured output for PDF/image form input | Purchasing | Configured provider; consent, timeout and validation | procurement/extraction.py
11.4 | Document input | Human review | Map source lines and confirm currency and prices | Purchasing | Server requires explicit review confirmation | frontend/src/features/purchasing/quotation-form.tsx
11.5 | Document input | Failure recovery | Keep manual input usable after extraction failure | Purchasing | Failure leaves source and manual form available | tests/test_v4.py